## 4px - Gantt Chart
PROJECT TITLE |  | ARPY (Augmented Reality Python) |  | COMPANY NAME |  | 4px (Four Pixel)
PROJECT MANAGER |  | Satrio Aji Nugroho |  | PROJECT START DATE |  | 2025-07-03
WBS | TASK TITLE | TASK DESCRIPTION | Tools | TASK OWNER | PCT OF TASK COMPLETE | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
1 | Brainstorming
1.1 | Discussion 1 | Brainstorming Ide Project | Mirro | All | 100% | bar: 2025-07-03 W1
1.2 | Discussion 2 | Fix Project Ideas | Mirro | All | 100% | bar: 2025-07-03 W2
2 | Planning
2.1 | Research Paper | Research Relevant Journal & Articles |  | All | 100% | bar: 2025-07-03 W3 to 2025-07-03 W4
2.2 | Prepare Interview | Creating interview script |  | Metha Anastasya | 100% | bar: 2025-07-03 W4
2.3 | Interview 1 | Interview Student from SMKN 1 Jakarta |  | Metha Anastasya | 100% | bar: 2025-07-03 W5
2.4 | Define Interview | Define User Need & Requiremens |  | Metha Anastasya | 100% | bar: 2025-07-03 W5
2.5 | Interview 2 | Interview Student from Bina Sarana Informatika University |  | Satrio Aji Nugroho | 100% | bar: 2025-07-03 W5
2.6 | Define Interview | Define User Need & Requiremens |  | Satrio Aji Nugroho | 100% | bar: 2025-07-03 W5
3 | Project Requirement
3.1 | User Persona | Creating User Persona from Interview | Canva | M. Rizky Hadi Prawiro | 100% | bar: 2025-07-03 W5
3.2 | Emphaty Map | Creating Emphaty Map from Interview | Canva | Aditya Ataby Hidayat | 100% | bar: 2025-07-03 W5
3.3 | User Journey | Creating Screnario Uses of ARPY | Canva | Metha Anastasya | 100% | bar: 2025-07-03 W5
3.4 | Wireframe App | Creating Wireframe Draft of ARPY | Figma | Satrio Aji Nugroho | 100% | bar: 2025-07-03 W5
4 | Development
4.1 | Design Application | Crate User Interface & User Experience of ARPY | Figma | Satrio Aji Nugroho | 100% | bar: 2025-07-03 W6 to 2025-07-03 W8
|  |  | Adobe Illustrator | Aditya Ataby Hidayat | 100% | bar: 2025-07-03 W7 to 2025-07-03 W8
4.2 | Journal | Writing Journal of ARPY Research | Word | All | 100% | bar: 2025-07-03 W8 to 2025-07-03 W10
4 | Evaluation
4.1 | Quisionare | Creating Quisionare of UI/UX ARPY | Google Form | Metha Anastasya | 100% | bar: 2025-07-03 W9 to 2025-07-03 W10
|  |  |  | Satrio Aji Nugroho | 100% | bar: 2025-07-03 W9 to 2025-07-03 W10
|  |  |  | M. Rizky Hadi Prawiro | 100% | bar: 2025-07-03 W9 to 2025-07-03 W10
4.3 | Evaluation UI/UX | Define Evaluation Needs |  | All | 60% | bar: 2025-07-03 W11
4.4 | Design Application | Evaluate & Improving UI/UX Design | Figma | Satrio Aji Nugroho | 5% | bar: 2025-07-03 W12 to 2025-07-03 W14
|  |  |  | Aditya Ataby Hidayat | 5% | bar: 2025-07-03 W12 to 2025-07-03 W14
|  |  |  | Metha Anastasya | 5% | bar: 2025-07-03 W12 to 2025-07-03 W14
5 | Exhibition
5.1 | Prepare Exhibition | Quality Control of ARPY Project |  | All | 0% | bar: 2025-07-03 W15
5.2 | Submit Exhibition | Submitting ARPY to Taman Ismail Marzuki Exhibition |  | All | 0% | bar: 2025-07-03 W16